## WP
SUMMARY STATISTICS
| Sample Size (n) : | 10000
CENTRAL TENDENCIES
Mean |  | Median
StErr
SPREAD
StDev: | 2.9
Max: | 23.49 | Q(.75):
Min: | -4.23 | Q(.25):
Range: | 27.72 | IQ Range: | 0
SHAPE
Skewness
Kurtosis
QUARTILES, PERCENTILES, INTERVAL
| 90% Interval |  | 95% Interval
Q(.05): |  | Q(.025):
Q(.95): |  | Q(.975):
Alpha (a): |  | Q(a/2):
% Interval: |  | Q(1-a/2):
PROBABILITIES
| REMAINING DURATION | 3.72 | MONTHS
|  | OVERALL PROJECT SCHEDULE IMPACT UNCERTAINTY: | 59.52%
|  | PROBABILITY OF COMPLETING PER SCHEDULE : | 18.3%
|  | TIMELY COMPLETION PROBABILITY: | 18.3%
|  | ESTIMATED EARLY COMPLETION DATE : | 2022-09-30
|  | ESTIMATED LATEST COMPLETION DATE : | 2024-01-31
HISTOGRAM PLOT
Min: | -9.23
Max: | 28.49
N: | 10000
Bins | Count | Scaled | Cum
-4.2336 | 0 | 0 | 0%
-2.8472 | 0 | 0 | 0%
-1.4609 | 0 | 0 | 0%
-0.074557 | 6 | 0.00043279 | 0.06%
1.3118 | 15 | 0.001082 | 0.21%
2.6981 | 62 | 0.0044722 | 0.83%
4.0845 | 231 | 0.016663 | 3.14%
5.4708 | 473 | 0.034118 | 7.87%
6.8572 | 955 | 0.068886 | 17.42%
8.2435 | 1485 | 0.10712 | 32.27%
9.6299 | 1878 | 0.13546 | 51.05%
11.0162 | 1809 | 0.13049 | 69.14%
12.4026 | 1425 | 0.10279 | 83.39%
13.7889 | 922 | 0.066506 | 92.61%
15.1752 | 484 | 0.034912 | 97.45%
16.5616 | 169 | 0.01219 | 99.14%
17.9479 | 66 | 0.0047607 | 99.8%
19.3343 | 17 | 0.0012262 | 99.97%
20.7206 | 3 | 0.0002164 | 100%
22.107 | 0 | 0 | 100%
23.4933 | 0 | 0 | 100%
CONFIDENCE LEVEL
Q | Confidence level | Variance | Contingencies
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72
3.72